## Sheet1
Employee ID | Employee Name | Date | Login Time | Logout Time | Task | Priority | Task Status | Completion % | Today's Work | Pending Task | Pending Reason | Next Step | Expected Date | Dependency / Help Needed | Time Spent on Task | Remarks | Estimated Time | Actual Time | Waiting Time | Reason for Delay | Task Source | Work Type | Carry Forward | Priority Changed? | Tomorrow's Priority
rabiya001 | Rabiya Tazeem Sana | 2026-09-09 | 10:42 | 18:15 | Student Performance Analysis | P1 | Completed | ~60% | Identified required student data fields, KPIs and planned the analysis workflow. | Further analysis and dataset preparation pending | Continue with dataset structure and KPI calculation | Continue with dataset structure and KPI calculation |  | No | 3.5 hrs | Completed | 3 hrs | 3.5 hrs | 0 | — | Badri Sir | Analysis | Yes | No | P1 – Student Performance Analysis
rabiya001 | Rabiya Tazeem Sana | 2026-09-09 | 10:42 | 18:15 | Employee daily tracker | P2 | Completed | 100% | Prepared | — | — | — | 2026-09-09 | No | 1 hr | Completed | 2 hrs | 1 hr | 0 | — | Badri Sir | Tracker Creation | No | No | N/A
rabiya001 | Rabiya Tazeem Sana | 2026-09-09 | 9:27
rabiya001 | Rabiya Tazeem Sana | 2026-09-10 | — | — | Daily Tracker Progress | P2 | Completed | 100% | Completed and updated the daily progress tracker. | — | — | Continue daily tracker updates | 2026-09-10 | No | 1 hr | Completed | 1 hr | 1 hr | 0 | — | Self | Tracker Creation | No | No | N/A
rabiya001 | Rabiya Tazeem Sana | 2026-09-10 | — | — | Employee Tracker | P2 | Completed | 100% | Prepared and completed the employee tracker. | — | — | Continue maintaining employee tracker | 2026-09-10 | No | 1 hr | Completed | 1 hr | 1 hr | 0 | — | Self | Tracker Creation | No | No | N/A
rabiya001 | Rabiya Tazeem Sana | 2026-09-11 | — | — | Review of Documents | P1 | Completed | 100% | Reviewed the documents sent by Badrinath Sir. | — | — | Await further documents/tasks from Badrinath Sir | 2026-09-12 | Badri Sir | As required | Completed | As required | As required | 0 | — | Badri Sir | Document Review | No | No | Await further task/document
rabiya001 | Rabiya Tazeem Sana | 2026-09-12 | — | — | Review of Documents | P1 | Completed | 100% | Reviewed the documents sent by Badrinath Sir. | — | — | Await further documents/tasks from Badrinath Sir | 2026-09-12 | Badri Sir | As required | Completed | As required | As required | 0 | — | Badri Sir | Document Review | No | No | Await further task/document
rabiya001 | Rabiya Tazeem Sana | 2026-09-13 | — | — | No Task | — | Not Applicable | 0% | Sunday — no work assigned. | — | Sunday | — | 2026-09-13 | — | 0 hrs | Sunday | 0 hrs | 0 hrs | 0 | — | — | — | No | No | Next working day
rabiya001 | Rabiya Tazeem Sana | 2026-09-14 | — | — | No Task Assigned | P3 | On Hold | 0% | No task assigned while documents were being reviewed; HRA login issue was also pending. | Further task assignment | Documents under review and HRA login issue | Wait for review completion and HRA login resolution | 2026-09-15 | HRA login / document review | 0 hrs | Awaiting task | 0 hrs | 0 hrs | Full day | HRA login issue and documents under review | Badri Sir | Waiting | Yes | No | Await task / HRA access
rabiya001 | Rabiya Tazeem Sana | 2026-09-15 | — | — | Review of Document | P1 | Completed | 100% | Reviewed the document sent by Badrinath Sir and was informed that another document would be sent by end of day. | Next document | Awaiting next document from Badrinath Sir | Review the next document when received | 2026-09-15 | Badrinath Sir | As required | Completed; awaiting next document | As required | As required | Partial day | Next document not yet received | Badri Sir | Document Review | Yes | No | Review next document
rabiya001 | Rabiya Tazeem Sana | 2026-09-16 | — | — | Student Performance Report | P1 | In Progress | In Progress | Worked on creating the student performance report and shared the required documents and videos with Badrinath Sir. | Further review / feedback | Awaiting feedback or further instructions | Continue student performance report as per reference/feedback | 2026-09-19 | Badri Sir / reference material | As required | Documents and videos shared for review | As required | As required | As required | Awaiting feedback | Badri Sir | Report Creation | Yes | No | Continue student performance report
rabiya001 | Rabiya Tazeem Sana | 2026-09-17 | — | — | Student Performance Report | P1 | In Progress | In Progress | Worked on creating the student performance report and shared the required documents and videos with Badrinath Sir. | Further review / feedback | Awaiting feedback or further instructions | Continue student performance report as per reference/feedback | 2026-09-19 | Badrinath Sir / reference material | As required | Documents and videos shared for review | As required | As required | As required | Awaiting feedback | Badri Sir | Report Creation | Yes | No | Continue student performance report
rabiya001 | Rabiya Tazeem Sana | 2026-09-18 | — | — | Student Performance Report | P1 | In Progress | In Progress | Worked on creating the student performance report and shared the required documents and videos with Badrinath Sir. | Further review / feedback | Awaiting feedback or further instructions | Continue student performance report as per reference/feedback | 2026-09-19 | Badri Sir / reference material | As required | Documents and videos shared for review | As required | As required | As required | Awaiting feedback | Badri Sir | Report Creation | Yes | No | Continue student performance report
rabiya001 | Rabiya Tazeem Sana | 2026-09-19 | — | — | Student Performance Report – Reference | P1 | In Progress | In Progress | Received the reference idea for the student performance report from Badrinath Sir. | Further work on report | Reference received; further instructions may be required | Use the shared reference to continue report preparation | 2026-09-19 | Badri Sir | As required | Reference idea received | As required | As required | 0 | — | Badri Sir | Report Creation | Yes | No | Continue report using reference
rabiya001 | Rabiya Tazeem Sana | 2026-09-20 | — | — | No Task | — | Not Applicable | 0% | Sunday — no work assigned. | — | Sunday | — | 2026-09-20 | — | 0 hrs | Sunday | 0 hrs | 0 hrs | 0 | — | — | — | No | No | Next working day
rabiya001 | Rabiya Tazeem Sana | 2026-09-21 | — | — | Student Performance Report – Sample Reports | P1 | Completed | 100% | HRA login issue was encountered; submitted Sample Report 1 and Sample Report 2. | Further changes / instructions | HRA login issue | Use the approved sample/reference for further work | 2026-09-21 | HRA login / review | As required | Sample reports 1 and 2 submitted | As required | As required | Partial day | HRA login issue | Badri Sir | Report Creation | Yes | No | Continue using sample/reference
rabiya001 | Rabiya Tazeem Sana | 2026-09-22 | — | — | Student Performance Report – Sample 2 | P1 | In Progress | In Progress | HRA login issue continued; was informed to use Sample 2 and work on it. | Further task/feedback | HRA login issue and awaiting further instructions | Continue work using Sample 2 | 2026-09-22 | HRA login / Badri Sir | As required | Instruction received to use Sample 2 | As required | As required | Partial day | HRA login issue | Badri Sir | Report Creation | Yes | No | Continue Sample 2
rabiya001 | Rabiya Tazeem Sana | 2026-09-23 | — | — | Awaiting Further Task | P3 | Waiting | 0% | Awaiting further tasks; no new task was assigned. | Further task assignment | No task assigned | Follow up / begin next assigned task | 2026-09-23 | Task assignment | 0 hrs | No task assigned | 0 hrs | 0 hrs | Full day | Awaiting further task | Badri Sir | Waiting | Yes | No | Await further task
rabiya001 | Rabiya Tazeem Sana | 2026-09-24 | — | — | Awaiting Further Task | P3 | Waiting | 0% | Awaiting further tasks; no new task was assigned. | Further task assignment | No task assigned | Follow up / begin next assigned task | 2026-09-24 | Task assignment | 0 hrs | No task assigned | 0 hrs | 0 hrs | Full day | Awaiting further task | Badri Sir | Waiting | Yes | No | Await further task
rabiya001 | Rabiya Tazeem Sana | 2026-09-25 | — | — | Awaiting Further Task | P3 | Waiting | 0% | Awaiting further tasks; no new task was assigned. | Further task assignment | No task assigned | Follow up / begin next assigned task | 2026-09-25 | Task assignment | 0 hrs | No task assigned | 0 hrs | 0 hrs | Full day | Awaiting further task | Badri Sir | Waiting | Yes | No | Await further task
rabiya001 | Rabiya Tazeem Sana | 2026-09-26 | — | — | Awaiting Further Task | P3 | Waiting | 0% | Awaiting further tasks; no new task was assigned. | Further task assignment | No task assigned | Follow up / begin next assigned task | 2026-09-26 | Task assignment | 0 hrs | No task assigned | 0 hrs | 0 hrs | Full day | Awaiting further task | Badri Sir | Waiting | Yes | No | Await further task
rabiya001 | Rabiya Tazeem Sana | 2026-09-27 | — | — | No Task | — | Not Applicable | 0% | Sunday — no work assigned. | — | Sunday | — | 2026-09-27 | — | 0 hrs | Sunday | 0 hrs | 0 hrs | 0 | — | — | — | No | No | Next working day
rabiya001 | Rabiya Tazeem Sana | 2026-09-28 | — | — | Student Performance Report | P1 | Completed | 100% | Completed the student performance report task assigned by Ravi Sir by 3:00 p.m. Shared the video and GitHub link for review. | Review / feedback | Awaiting review by Ravi Sir | Address any feedback after review | 2026-09-28 | Ravi Sir | Completed by 3:00 p.m. | Completed and submitted for review | As assigned | As assigned | After 3:00 p.m. | Awaiting review | Ravi Sir | Report Creation | No | No | Await review / next task
rabiya001 | Rabiya Tazeem Sana | 2026-09-29 | — | — | Employee Performance Report | P1 | In Progress | 0% | Task assigned by Ravi Sir to create the employee performance report. | Employee performance report | Task newly assigned | Start and complete employee performance report | 2026-09-29 | Ravi Sir | In progress | New task assigned | As assigned | In progress | 0 | — | Ravi Sir | Report Creation | Yes | No | P1 – Employee Performance Report
rabiya001 | Rabiya Tazeem Sana | 2026-09-30 | - | - | Employee Performance Report | P1 | Completed | 100% | Task assigned by Ravi Sir to create the employee performance report. | Employee performance report | Task newly assigned | Review the documents and structure | 30SEP (EOD) | Ravi Sir | Completed by EOD | New task assigned
rabiya001 | Rabiya Tazeem Sana | 2026-10-01 | - | - | Corrections in Review of Documents | P1 | In Progress | 100% | Corrections in the reviews as infromed by Ravi Sir | Employee performance report | Due to the corrections andd proper review of the documents | Prepared a new KPI/KPA structure | 2026-10-01 | Ravi Sir | Completed on same day | Awaiting for reply
rabiya001 | Rabiya Tazeem Sana | 02-0CT-2026 | - | - | Updated KPI/KPA Document shared | P1 | Completed | 100% | Documents reviewd and accepted by Ravi Sir | Collect Employees Details | Excel Sent for the Details | Collect,organize and create python code | - | Ravi Sir | Awaiting for the excel update | Awaiting
rabiya001 | Rabiya Tazeem Sana | 2026-10-03 | - | - | Waiting for Excel sheet details | P1 |  |  | - | Collect Employees Details | Excel Sent for the Details | Collect,organize and create python code | - | Ravi Sir | Awaiting for the excel update | Awaiting
rabiya001 | Rabiya Tazeem Sana | 2026-10-04 | - | - | - | P1 |  | - | - | - | - | - | - | - | - | -
rabiya001 | Rabiya Tazeem Sana | 05-0ct-2026 | - | - | Received The Excel Details | P1 | Completed | 100% | Organize the data | Create python code | - | Create python code | - | Ravi Sir | - | In progress
rabiya001 | Rabiya Tazeem Sana | 2026-10-06 | - | - | Creating python code with the data | P1 | In Progress | 50% | Organized the data,Writing python code for the data | Completion of python code | In progress | 100%,error free code for the data and to be given for review | - | Ravi Sir | - | In progress | [5 empty] | Development | Yes | No
rabiya001 | Rabiya Tazeem Sana | 2026-10-07 | - | - | Creating python code with the data | P1 | In Progress | 30% | Organized the data,Writing python code for the data | Completion of python code | In progress | 100%,error free code for the data and to be given for review | 08-0CT-2026 | Ravi Sir | - | In progress |  |  |  | IN PROGRESS |  | Development | Yes | No
rabiya001 | Rabiya Tazeem Sana | 2026-10-08 | - | - | Organized the data,completed code writing | P1 | Completed | 100% | Completed code and submitted for review | Done | Completed | Awaiting for Ravi Sir's Review and further steps | - | Ravi Sir | - | Completed
rabiya001 | Rabiya Tazeem Sana | 2026-10-09 | LEAVE | -
rabiya001 | Rabiya Tazeem Sana | 10-0CT-2026 | - | - | Awaiting for the review | P1 | Completed
rabiya001 | Rabiya Tazeem Sana | 2026-10-11 | SUNDAY | -
rabiya001 | Rabiya Tazeem Sana | 12-0ct-2026 | - | - | Employee Tracking Dashboard,Student Performance Dashboard | P1 | In Progress | In Progress | Started Developing dashboards for employee tracking data analysis and student performance visualization | Complete dashboard development and testing | Development in Progress | Add employee-wise analytics,student serach by name/roll/number/grade/section, visualizations,and individual student report printing | 2026-10-12
rabiya001 | Rabiya Tazeem Sana | 2026-10-13 | - | -
rabiya001 | Rabiya Tazeem Sana | 14-0ct-2026 | - | -
rabiya001 | Rabiya Tazeem Sana | 15-0ct-2026 | - | -